## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2231-swen-261-04-7G-Team7
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a helper I want to see a list of needs so that I choose what to contribute to. | Given that I am on the u-fund site when I am not on the Needs page then I must see a means to navigate to the Needs page.
Given that I am not on the Needs page when I choose the Needs page then I am taken to the Needs page.
Given that I am on the Needs page when there are no needs in the cupboard I see a message indicating that that there are no needs available to contribute.
Given that I am on the Needs page when there are needs in the cupboard then I see each need and short description.
Given that I am on the Needs page when there are needs in the cupboard then I see a means to add each need to my funding basket.
AS a Developer I WANT to submit a request to get the the needs in the cupboard whose name contains the given text, SO THAT I have access to only that subset of needs. | GIVEN I submit a request for the need THEN the system should return the cost, quantity, and type for the product with a status code of 200 (OK)
AS a Developer I WANT to submit a request to create a new need (name [unique], cost, quantity, type) SO THAT it is added to the cupboard. | GIVEN I submit a **need **object WHEN no **need **with the given name exists THEN the system should create the **need**, add it to the **cupboard**, save to the persistent storage, and return the **need **object and a status code of 201 (CREATED)
GIVEN the need I want to delete does not exist WHEN I request to delete that need THEN the syGIVEN I submit a **need **object WHEN a **need **with the given name already exists THEN the system should return a status code of 409 (CONFLICT)stem should return a status of NOT FOUND (404)
AS a Developer I WANT to submit a request to get the entire cupboard SO THAT I have access to all of the needs for the organization. | GIVEN I submit a request for the inventory WHEN products exist in the inventory THEN the system should return a list of products and a status code of 200 (OK)
GIVEN I submit a request for the inventory WHEN no products exist in the inventory THEN the system should return an empty list of products and a status code of 200 (OK)
As a Developer I want to submit a request to delete a single need SO THAT it is no longer in the cupboard | GIVEN that I want to delete a need from the cupboard WHEN product already exists / run out, THEN the product will be deleted
AS a Developer I WANT to submit a request to get a single need SO THAT I can access the cost, quantity and name. | GIVEN I submit a request for the need THEN the system should return the cost, quantity, and type for the product with a status code of 200 (OK)
AS A Developer I WANT to submit a request to get the cupboard SO THAT I can update needs in the cupboard. | 1. GIVEN I submit a request for the inventory WHEN products exist in the inventory THEN the system should return a list of products and a status code of 200 (OK)
2. GIVEN I submit a request for the inventory WHEN no products exist in the inventory THEN the system should return an empty list of products and a status code of 200 (OK)
As a Helper I want to be able to submit my cart so that I can clear my cart. | **Given** there are needs in the cart, **when** I click submit **then** I expect the needs to be cleared
As a Helper I want to submit my cart so that I confirm my purchase. | **Given** SOME PRECONDITION **when** I DO SOME ACTION **then** I EXPECT SOME RESULT.
**Given** I want to submit my cart, **when** I click the submit button (calls api endpoint) **then** I expect to have my cart submitted (clear)
As a Helper I want to be able to call the api so that I can I get a list of needs in the cart. | **Given** user calls api **then** I get a list of needs from the cart.
As a Helper I want to be able to add a need to the cart so that the need is added to the cart. | **Given** I have needs, **when** I press a button to add a need to the cart **then** I expect that need to be added to the cart
As a Helper I want to see a list of needs so that I can choose what I want to purchase | **Given** I am on the main needs page, **when** I load the page **then** I expect to see a list of needs and descriptive information.
As a Helper I want to be able to search for needs and have a list of needs that match my search show only. | **Given** I want to search, **when** I enter text in the search bar **then** I expect to see a list of needs that contain the word I searched for.
As a Helper I want to add things to the basket so that I can ensure that Admin knows that I’m providing the help. | GIVEN that I want to add an item to cart WHEN I want to buy a item THEN the item will be added to the cart
As a Helper I want to remove things from the basket so that if I accidentally put things into the basket that I don’t intend to do so I can remove it and return it to the list. | GIVEN that I want to remove an item from basket WHEN I do not want to buy / accidently added the item THEN the item will be removed from basket
As a Helper I want to see a list of needs in my cart so that I can see what is in my cart. | **Given** SOME PRECONDITION **when** I DO SOME ACTION **then** I EXPECT SOME RESULT.
**Given** there are needs in the cart, **when** I go to the cart **then** I expect to see a list of needs.
As a Helper I want to remove a need from the cart so that I don’t have to look at it anymore. | **Given** there are needs in the cart, **when** I try to delete a need **then** I expect it to go away.